## Slide 1: Agile Framework
Sample Courseware Contents

## Slide 2
© 360PMO Project Management Consulting, Inc.

## Slide 3: Learning Objectives
At the conclusion of this lesson, students will be able to:
Explain the Agile mindset
Describe situations where Agile best fits
List the benefits of using Agile
Know the origin/history of Agile
Demonstrate an understanding of the Agile Manifesto, Values, Principles and Practices
Compare traditional vs. Agile project management methods
Identify high-level differences from one Agile method to another

## Slide 4: What is Agile?
Methodology?
Framework?
No Documentation !
No Design…
Process?
Approach?
No Discipline
No Planning!
Iterative
Another Fad
…Silver Bullet

## Slide 5
4 AGILE VALUE
12 AGILE PRINCIPLES
MANY AGILE PRACTICES
Individuals and interactions over processes and tools
Working software over comprehensive documentation
Our highest priority is to satisfy the customer through early and continuous delivery of valuable software.
Welcome changing requirements, even late in development. Agile processes harness change for the customer's competitive advantage.
Deliver working software frequently, from a couple of weeks to a couple of months, with a preference to the shorter timescale.
Business people and developers must work together daily throughout the project.
Build projects around motivated individuals. Give them the environment and support they need, and trust them to get the job done.
Time-boxing
Retrospective
Spike Solution
Planning Poker
Backlog Prioritization
Progress Elaboration
Minimal marketable Features
Personas
Story Mapping
User Stories
Product Backlog
Visualize Workflow
Wireframe
Daily Stand-up
Limit Work in Progress (WIP)
Avoid Waste
Short Iterations
Sprint Goals
Servant Leader
Self -organization
Team Agreements
Release Goals
Release Plan
Project Chartering
Quality Assurance
Refactoring
Relative Sizing
Product Vision
Doing Agile……
Being Agile……
Pair Programming
Face to Face Conversation
Osmotic Communication
Test Driven Development (TDD)
Velocity
Unit Testing
Test First Development
Technical Debt
Task board
Swarming
Regression Test
Minimum Viable Product
Last Responsible Moment (LRM)
……..
Customer collaboration over contract negotiation
Responding to change over following a plan
The most efficient and effective method of conveying information to and within a development team is face-to-face conversation.
Working software is the primary measure of progress.
Agile processes promote sustainable development. The sponsors, developers, and users should be able to maintain a constant pace indefinitely.
Continuous attention to technical excellence and good design enhances agility.
Simplicity--the art of maximizing the amount of work not done--is essential.
The best architectures, requirements, and designs emerge from self-organizing teams.
At regular intervals, the team reflects on how to become more effective, then tunes and adjusts its behavior accordingly.

## Slide 6: What’s Different?
Traditional | Agile
Defined process: Control and Coordinated | Empirical process: Inspect and Adapt
Work is organize around the team | Team organize around work
Work is assigned or push to the team | Work is store in queue and team pull the tasks
Plan all in advance | Plan as you go
Work breakdown structure | Feature breakdown structure
Functional specs | User stories
Gantt chart | Release plan
Status report | Information radiators/deliver as you go
Learn at the end | Learn every iteration
Follow the plan | Adapt everything
Manage task | Manage team
Conventional project team | Self-organized project teams
Avoid change | Embrace change
Prescriptive | Adaptive

## Slide 7: Multiple Level of Planning
Roadmap
Release
Iteration
Daily
Vision
Planning Onion

## Slide 8: User Story Template
I want/would like/should/can <Function>
Who?
What?
Why?
As a <ROLE>,
So that <BUSINESS VALUE/BENEFIT>

## Slide 9: Factors in Backlog Prioritization
USER STORY
1
USER STORY
2
USER STORY
3
SPIKE
4
USER STORY
5
USER STORY
6
USER STORY
7
DEFECT
8
USER STORY
9
SPIKE
10
USER STORY
11
USER STORY
12
USER STORY
13
DEFECT
14
Dependencies
Risk
Value
Resources
Cost
Knowledge

## Slide 10: Operating Model of Agile Team
Team organized around the work
Empowered
Self organize / Self managed
Team pulls the task from queue /backlog
Cross functional
Intensely collaborative
Work is organized around the team
Tasks are assigned (most of the time by the PM)
Functional silos
Functional Teams
Agile Teams
Project Manager
Coach/Facilitator
Business Analyst
Testers/QA
Customer
Product Owner
Product Manager
Developer
Support Engineer
Cross functional Teams

## Slide 11
Activity: Sequence the Scrum Events

## Slide 12: Sequence the Scrum Events
Iteration 1
Iteration 2
Release
Retrospective 1
2 Weeks
2 Weeks
Sprint 1 Review
Daily Stand-up
Sprint 1 Planning
Release Planning
Product Backlog Refinement
Retrospective 2
Sprint 2 Review
Sprint 2 Planning
5 Minutes
Product Backlog Creation

## Slide 13
Activity: Match the Definitions

## Slide 14: Match the Definitions
1 | Product Development
2 | Product Owner
3 | Scrum Master
4 | Customer
5 | Product Vision
6 | Product Increment
7 | Sprint Backlog
8 | Product Backlog
9 | Definition of Done
10 | Release
11 | Sprint
12 | Sprint Planning
13 | Daily Scrum
14 | Sprint Review
15 | Sprint Retrospective
16 | Release Planning
10 Minutes
A | The means to reach the Product Vision
B | what it takes to have a Product Backlog item done
C | meeting to improve the work of the Scrum team
D | delivery of product increment(s) to the customer
E | the one defining the product
F | the ones getting frequent ROI and providing feedback
G | the Sprint plan
H | meeting to get feedback on the product
I | meeting to plan the next day
J | what is the overall need to be supplied
K | the ones building the product
L | valuable slice of the product produced in a Sprint
M | meeting to plan the next Release
N | the facilitator and Scrum process coach
O | the development cycle
P | meeting to plan the current Sprint

## Slide 15: Test Driven Development (TDD)
In TDD, a programmer writes a test before they write any code. The test fails and the programmer writes just enough code to make it pass. This cycle is repeated on timelines of every few minutes.
Test -> Code -> Refactor
REFACTOR
RED
GREEN
1. Add a Test
2. Make it work
3. Make it clean

## Slide 16: 5 Phases of Retrospective
Set the Stage
1
Gather Data
2
Generate Insight
3
Decide what to do
4
Close the retrospective
5

## Slide 17: High Level Process Map
Iteration n
Iteration 3
Iteration 2
Feasibility
Project Visioning
Initiation
Release Planning
Iteration 1
Close Out
NPV, IRR, ROI
Business Case with High level Estimates
Project
Charter
Product Backlog
High level estimating using affinity
Product Roadmap
Epic
Stories
Stories
Estimating Using Planning Poker
Theme
L
M
S
XL
Release Plan
Final Product Increment
Testing Agreement
Team Environment
Architecture approach
Dependencies
Risks
Iteration Backlog
Task Board
Go back to Release Planning for another release, or if final release, go to project closeout
Backlog
To Do
In Progress
Done
Iteration Planning
Release
Daily stand-up, Development, Testing, deployment, etc.
Retrospective
Review
Burn up/down
Iteration 0
Next Iteration
Higher Priority
Lower Priority
Increment
Envisioning
Speculate
Explore | Adapt
Close
Iteration Task

## Slide 18
Group Discussion
Handling Defects in Agile Projects

## Slide 19: How to Handle Defects
Discuss the best approach for dealing with bugs in Agile projects:
Should they be placed on the product backlog or in a separate bug list?
If they’re on the backlog, does the product owner get to set their priorities, or are they automatically the most important items For next sprint
Should there be a separate bug fixing iteration/sprint?
15 Minutes

## Slide 20
Test Your Knowledge

## Slide 21: Test Your Knowledge
Mark is assigned as a Scrum Master to the newly launched agile team. He is being asked to provide the list of metrics to measure the progress. Which metric will she provide as a primary measure of progress?
Velocity.
Team Satisfaction.
Working software.
Customer satisfaction.
Notes: Answer C) According to Agile Manifesto principles, “working software is the primary measure of progress”.

## Slide 22: Test Your Knowledge
Mark is assigned as a Scrum Master to the newly launched agile team. He is being asked to provide the list of metrics to measure the progress. Which metric will she provide as a primary measure of progress?
Velocity.
Team Satisfaction.
Working software.
Customer satisfaction.

## Slide 23: Lesson Review
What is Agile?
Name five benefits of Agile
List any five Agile methods.
What are the four values of Agile?
What are the differences between pull and push-based systems?
Describe any four principles of the Agile Manifesto

## Slide 24: Lesson Review (continue..)
Which methodology is more prescriptive RUP or Scrum?
Name two influencers who authored the Agile Manifesto in 2001
When was the first time an iterative and incremental approach was used in software development?
List five differences between traditional waterfall and Agile
What is inspect and adapt and how it is different from control/coordinated?

## Slide 25
Following references are used in the preparation of this lecture.
Abstracted from Shuh, Peter (2005). Integrating Agile Development in the Real World
How sustainable is your agile transformation to sustainable organizational agility, Ahmed Sidky
Strategic Management and Organizational Dynamics by Ralph Stacey in Agile Software Development with Scrum by Ken Schwaber and Mike Beedle
Planning Onion, “Agile Estimating and Planning” By: Mike Cohn
Iterative and incremental development by Craig Larman, victor Basili
What’s the big fuss about Agile? by Ahmed Sidky
Manifesto for Agile Software Development
Principles behind the Agile Manifesto
Agile Retrospectives: Making Good Teams Great Esther Derby, Diana Larsen

## Slide 26
All registered and unregistered trademarks (service marks, brands, icons, copyrights etc.) mentioned on this course are the property of their respective owners.
Content that references these trademarks is not sponsored by, endorsed by, or affiliated with the respective trademark owners. PMI-ACP®, PMBOK®, PMI®, and PMP® are either marks or registered marks of the Project Management Institute, Inc.

## Slide 27
360PMO

## Slide 28
www.360pmo.com